## Sprint Task Tracker
Story ID | User Story | Sprint | Assigned To | Start Date | Due Date | Status | Priority | Notes
US-01 | As a user, I want to register/login so that I can access my account. | Sprint 1 | Frontend Developer | 2026-09-15 | 2026-09-19 | Completed | High | Basic email/password auth
US-02 | As a user, I want to browse products by category so that I can find what I need. | Sprint 1 | Backend Developer | 2026-09-15 | 2026-09-22 | Completed | High | Category API + listing page
US-03 | As a user, I want to add products to cart so that I can purchase them later. | Sprint 1 | Frontend Developer | 2026-09-18 | 2026-09-26 | In Progress | High | Cart state persistence pending
US-04 | As a user, I want to make payments securely so that I can complete my order. | Sprint 2 | Backend Developer | 2026-09-29 | 2026-10-06 | Not Started | High | Mock payment gateway integration
US-05 | As a user, I want to track my order status so that I know when it will arrive. | Sprint 2 | Backend Developer | 2026-09-29 | 2026-10-08 | Delayed | Medium | Blocked on order-status API design
US-06 | As a user, I want to view my order history so that I can reorder easily. | Sprint 2 | Frontend Developer | 2026-10-01 | 2026-10-08 | Not Started | Medium | Depends on US-05
US-07 | As a QA tester, I want to test the checkout flow so that payment errors are caught early. | Sprint 2 | QA Tester | 2026-10-06 | 2026-10-10 | Not Started | High | Blocked until US-04 completes
US-08 | As a Project Lead, I want a UI/UX design review so that the app is consistent before dev. | Sprint 1 | UI/UX Designer | 2026-09-15 | 2026-09-18 | Completed | Medium | Wireframes approved

## Summary
Sprint Progress Summary
Status | Count
Completed | 3
In Progress | 1
Not Started | 3
Delayed | 1
Total Stories | 8
% Completed | 37.5%